## CEO Summary
Zarthi webinar: 200 live attendees from Google, Meta and LinkedIn ads only
One-page summary for the CEO. All numbers update automatically from the Inputs tab.
The answer in 5 numbers
People who attend LIVE (goal) | 200
Registrations we must buy with ads | 800
Total budget, everything included | 594120
Cost per live attendee | 2970.6
Time needed | 7 weeks (1 setup + 5 ads + live day + 1 follow-up)
Total budget in lakh | 5.9412
Where the money goes
Platform | Registrations | Ad spend (₹) | Cost per registration (₹) | % of ad spend | Its job
Meta | 480 | 117000 | 243.75 | 27.27% | Volume: cheapest registrations, mixed quality
LinkedIn | 160 | 208000 | 1300 | 48.48% | Quality: reaches the exact job titles we want
Google | 160 | 104000 | 650 | 24.24% | Intent: people already searching cloud cost topics
Total ad spend | 800 | 429000 | 536.25 | 100%
+ GST, test buffer, tools, lucky draw |  | 165120
Total budget |  | 594120
How it works, in 4 steps
1. Week 1 TEST: run small budgets on many ads to learn the real cost per registration on each platform.
2. Weeks 2–4 SCALE: stop the losers and put the money on the winning ads and audiences.
3. Week 5 FINAL PUSH: countdown ads and 8 reminders by email, WhatsApp and phone so registrants actually show up.
4. Live day + Week 6: run the webinar, then offer a free cloud cost assessment and hand warm leads to sales within 72 hours.
Being realistic: the 3 biggest risks
1. Show-up: people from ads forget. At 20% show-up instead of 25% we need ~1,000 registrations and more budget (see the What-If tab).
2. Costs are estimates: this is the first webinar, so costs are based on industry benchmarks. Week 1 gives our real numbers and we update this file.
3. Meta brings volume but some low-quality sign-ups. LinkedIn keeps the audience senior. We check audience quality daily.
Decisions needed from the CEO to start
☐ Approve the total budget shown above
☐ Pick the webinar date and time (at least 7 weeks from approval)
☐ Approve the webinar title and topic
☐ 2 hours of CEO + CTO time to shoot the ad videos
☐ OK to run LinkedIn ads from CEO/CTO posts (Thought Leader Ads)
☐ Define "200": peak live viewers at one time or total unique people who joined

## Inputs
Inputs: change the yellow cells, everything else updates
Blue text on yellow = an assumption you can edit. Black = formula. Green = pulled from another tab.
A. Goal and show-up
Assumption | Value |  |  |  |  | Why this number (source / logic)
Target: people who attend LIVE | 200 |  |  |  |  | Your goal. Decide with the CEO whether 200 means peak concurrent viewers or total unique joiners (this plan uses total unique joiners).
Show-up rate (registered → attend live) | 25% |  |  |  |  | Industry median is 41.6% and the bottom quarter is 28.4% (analysis of 12,400 B2B webinars, 2026). Cold paid-ad traffic shows up less, so we plan at 25%.
Stay till the end (of live attendees) | 65% |  |  |  |  | Planning estimate for a 60-min session with the live bill teardown at the end.
Book a free assessment (of those who stayed) | 12% |  |  |  |  | Planning estimate for a first webinar. Replace with real data afterwards.
GST on ad spend | 18% |  |  |  |  | 18% GST on Indian invoices from Meta, LinkedIn and Google.
Test buffer (% of ad spend) | 10% |  |  |  |  | Money spent on ads that lose in test week. This is the price of learning real costs.
Webinar platform licence, 500 seats (₹) | 15000 |  |  |  |  | Estimate for one month of a 500-seat plan. Confirm with a quote.
Reminder tools: email + WhatsApp API (₹) | 10000 |  |  |  |  | Estimate for ~800 contacts × 8 reminders. Confirm with a quote.
Lucky draw for people who stay till the end (₹) | 20000 |  |  |  |  | 10 × ₹1,000 + 2 × ₹5,000 vouchers. Optional: set to 0 to remove. Helps show-up.
B. Campaign assumptions (only Google, Meta and LinkedIn ads)
Campaign | Platform | Share of registrations | Cost per registration (₹) | Click-through rate (CTR) | Form / page conversion | Why this number (source / logic)
Meta: new audience (FB + Instagram) | Meta | 52.5% | 250 | 1% | 12% | Volume engine. Cheapest registrations but lower quality. ₹250 is a planning estimate for India B2B webinar lead forms; test week gives the real number.
Meta: retargeting (visited page / watched video) | Meta | 7.5% | 200 | 1.5% | 20% | People who already showed interest. Small but cheap. Planning estimate.
LinkedIn: job-title targeting (Lead Gen Form) | LinkedIn | 20% | 1300 | 0.6% | 12% | Quality engine: right job titles. LinkedIn India cost per lead is ₹850–₹2,500 (2026 benchmark); we plan mid-range.
Google: Search (people searching the topic) | Google | 10% | 800 | 4% | 15% | High intent but limited search volume in India for these keywords. Planning estimate.
Google: YouTube video ads | Google | 10% | 500 | 0.8% | 10% | CTO video shown to people searching cloud cost / AWS topics. Planning estimate.
Total (must be 100%) |  | 100% | OK
C. How ad money is spread over the 5 ad weeks
Week | What happens | % of ad spend |  |  |  | Why
Week 1 | TEST | 10% |  |  |  | Small budget, many ad versions. Find which ads and audiences give the cheapest registrations.
Week 2 | SCALE | 20% |  |  |  | Move money to winners. Raise budget on winners by ~20% every 3 days.
Week 3 | SCALE | 25% |  |  |  | Full speed on winners. Retargeting now has enough visitors.
Week 4 | SCALE | 25% |  |  |  | Full speed. Fresh ad versions to avoid fatigue.
Week 5 | FINAL PUSH | 20% |  |  |  | Countdown ads. People who register in the last 10 days show up the most.
Total (must be 100%) |  | 100% | OK

## Funnel
Reverse funnel: how many people we need at each step
Start from 200 live attendees and work backwards. All numbers are formulas.
Step | People | % moving to this step | What it means
1. See the ad (impressions) | 705492 |  | Total ad views needed across Google, Meta and LinkedIn.
2. Click the ad | 6466 | 0.9165% | People who click through to the form or landing page.
3. Register | 800 | 12.37% | To get 200 live at a 25% show-up rate we need this many registrations.
4. Attend LIVE (the goal) | 200 | 25% | This is the 200.
5. Stay till the end | 130 | 65% | These people see the offer and the lucky draw.
6. Book a free assessment / meeting | 16 | 12.31% | Sales pipeline created by the webinar.
In one line: about 1 in 4 people who register actually attend, so 200 live needs about 800 registrations, all bought through ads.

## Channel Plan
Channel plan and full budget
Registrations, ad spend, clicks and impressions per campaign. Edit assumptions on the Inputs tab.
Campaign | Platform | Registrations | Cost per registration (₹) | Ad spend (₹) | Clicks needed | Impressions needed | % of ad spend
Meta: new audience (FB + Instagram) | Meta | 420 | 250 | 105000 | 3500 | 350000 | 24.48%
Meta: retargeting (visited page / watched video) | Meta | 60 | 200 | 12000 | 300 | 20000 | 2.797%
LinkedIn: job-title targeting (Lead Gen Form) | LinkedIn | 160 | 1300 | 208000 | 1333 | 222167 | 48.48%
Google: Search (people searching the topic) | Google | 80 | 800 | 64000 | 533 | 13325 | 14.92%
Google: YouTube video ads | Google | 80 | 500 | 40000 | 800 | 100000 | 9.324%
Total |  | 800 | 536.25 | 429000 | 6466 | 705492 | 100%
Cost per registration in the Total row is the blended average across all campaigns.
Full budget (everything included)
Item |  |  |  | Amount (₹) |  |  | % of total
Ad spend: Google + Meta + LinkedIn |  |  |  | 429000 |  |  | 72.21%
GST on ad spend |  |  |  | 77220 |  |  | 13%
Test buffer (ads that lose in week 1) |  |  |  | 42900 |  |  | 7.221%
Webinar platform licence |  |  |  | 15000 |  |  | 2.525%
Reminder tools (email + WhatsApp) |  |  |  | 10000 |  |  | 1.683%
Lucky draw (optional) |  |  |  | 20000 |  |  | 3.366%
TOTAL BUDGET (all-in) |  |  |  | 594120 |  |  | 100%
Cost per LIVE attendee (all-in) |  |  |  | 2970.6
Cost per registration (all-in) |  |  |  | 742.65
By platform
Platform |  | Registrations | Cost per registration (₹) | Ad spend (₹) |  |  | % of ad spend
Meta |  | 480 | 243.75 | 117000 |  |  | 27.27%
LinkedIn |  | 160 | 1300 | 208000 |  |  | 48.48%
Google |  | 160 | 650 | 104000 |  |  | 24.24%
Total |  | 800 | 536.25 | 429000 |  |  | 100%

## Weekly Plan
Week-by-week plan: money, registrations and checkpoints
Ads run 5 weeks. Week 0 is setup, Week 6 is follow-up. Weekly % split is on the Inputs tab.
Week | Stage | Meta (₹) | LinkedIn (₹) | Google (₹) | Total ad spend (₹) | Daily spend (₹) | New registrations (target) | Total registrations so far | % of goal reached | Main jobs this week
Week 0 | SETUP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Lock title and date. Build landing page. Install Meta pixel, LinkedIn Insight Tag, Google tag + UTMs. Shoot CEO/CTO videos. Make 10–12 ads. Book webinar platform.
Week 1 | TEST | 11700 | 20800 | 10400 | 42900 | 6128.5714 | 80 | 80 | 10% | Run 3 hooks × 3 audiences on Meta, 2 × 2 on LinkedIn, 2 ad groups on Google. Check cost per registration daily.
Week 2 | SCALE | 23400 | 41600 | 20800 | 85800 | 12257.1429 | 160 | 240 | 30% | Switch off losing ads. Put money on winners. Turn on retargeting.
Week 3 | SCALE | 29250 | 52000 | 26000 | 107250 | 15321.4286 | 200 | 440 | 55% | Scale winners. Add 2 new ad versions. Monday update to CEO.
Week 4 | SCALE | 29250 | 52000 | 26000 | 107250 | 15321.4286 | 200 | 640 | 80% | Scale winners. Refresh tired ads (CTR falling). Monday update to CEO.
Week 5 | FINAL PUSH | 23400 | 41600 | 20800 | 85800 | 12257.1429 | 160 | 800 | 100% | Countdown ads (7 days / tomorrow / today). Reminder sequence running. Platform test call.
LIVE DAY | WEBINAR | [6 empty] | 200 |  | Tue/Wed/Thu, 4–5 pm IST. 60 minutes. Backup host ready.
Week 6 | FOLLOW-UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Same evening: assessment booking email. Recording to no-shows. Sales calls within 72 hours. Results review in 5 days.
Total |  | 117000 | 208000 | 104000 | 429000 |  | 800
Checkpoint rule: if 'Total registrations so far' is more than 20% behind target at the end of any week, use the test buffer to add budget to the best campaign and refresh ads.

## Targeting & Ads
Who we target and what ads we run
One row per campaign. Copy this into the ad accounts at setup.
Campaign | Who sees the ad (targeting) | Ad format | Ad message / hook | Where the click goes
Meta: new audience (FB + Instagram) | India metros (Bengaluru, Mumbai, Delhi NCR, Hyderabad, Pune, Chennai). Age 25–50. Interests: cloud computing, AWS, Microsoft Azure, DevOps, IT management. Exclude students/job seekers where possible. | 30-sec CTO talking-head video, 15-sec text reel, speaker card image, 5-slide carousel | "Your cloud bill keeps growing but traffic doesn't? Watch a CTO tear down real cloud bills, live." | Meta instant lead form (pre-filled) AND landing page: test both in week 1
Meta: retargeting | People who visited the landing page but did not register, watched 50%+ of a video, or opened the lead form without submitting. Last 30 days. | Countdown images (7 days / tomorrow / today), "X people registered" image | "Seats are filling. Live teardown of real cloud bills: [date], 4 pm." | Landing page
LinkedIn: job-title targeting | India. Job titles: IT Manager, Engineering Manager, Head of IT, Tech Lead, Cloud Architect, DevOps Manager, CTO, VP Engineering. Company size 200+. Exclude your own employees and competitors. | Single image (speaker card), document ad (5 CTO questions), 30-sec video. Thought Leader Ads from CEO/CTO posts if approved | "Your cloud bill is a leadership problem. The CTO decision framework, live, with real bill teardowns." | LinkedIn Lead Gen Form (pre-filled, 5 fields max)
Google: Search | India. Keywords: cloud cost optimization, reduce AWS bill, AWS cost reduction, cloud migration strategy, Azure cost management. Phrase + exact match. Negative keywords: jobs, course, free, certification, salary. | Responsive search ads, 3 ad groups by keyword theme. Sitelinks: Agenda, Speakers, Register. | "Free Live Webinar: Cut Your Cloud Bill ¦ CTO Framework + Live Bill Teardown" | Landing page
Google: YouTube video ads | India. Custom segment: people who searched cloud cost / AWS / Azure terms. Placements on tech and cloud channels. | 60-sec mini-lesson video (skippable in-stream) + 15-sec Shorts version | Give one part of the framework for free, "the rest is live on [date]" | Landing page
Landing page / form checklist (everything on the first screen)
1. Headline = webinar title. Sub-headline = the live cloud bill teardown promise.
2. Photos of CEO and CTO with a 2-line bio and client names (with permission).
3. Three bullets: what you will take away.
4. Form with only 5 fields: name, work email, phone, job title, monthly cloud bill (dropdown).
5. Thank-you page: Add to Calendar button, WhatsApp opt-in, invite-a-colleague link.
6. Clearly say: "No product demo. No sales pitch."

## Show-up Plan
Show-up plan: turning registrations into live attendees
Ads bring registrations. These reminders (no ad cost) decide whether we hit 200 live.
When | Channel | Message
Right after registering | Email + WhatsApp | Confirmation + calendar invite (.ics) + link to send your cloud bill question
7 days before | Email | Value teaser: one part of the framework, "full version live"
3 days before | Email | Agenda + "bills for the live teardown are being chosen"
1 day before | Email + WhatsApp | Reminder for tomorrow + lucky draw for those who stay till the end
1 day before | Sales team phone call | Personal call to the top 50 best-fit registrants (big cloud bill)
2 hours before | WhatsApp | Join link
15 minutes before | Email + WhatsApp | "We are going live"
5 minutes after start | Email + WhatsApp | To no-shows: "We have started, the teardown is at the end"
Rules: use the same join link in every reminder. Do NOT promise a recording in advance (it lowers live attendance). Send the recording to no-shows after.

## Rules
Daily rules: when to stop an ad and when to add money
Check ads every day. Change ads twice a week. Send the registration count to the CEO every Monday.
What we watch | Good (target) | Stop / alarm | What we do
Meta cost per registration | Below ₹250 | Above ₹450 after ₹2,000 spent | Stop that ad, move money to the winner
LinkedIn cost per registration | Below ₹1,300 | Above ₹2,000 after ₹5,000 spent | Stop that ad, change audience or image
Google Search cost per registration | Below ₹800 | Above ₹1,400 after ₹4,000 spent | Pause keyword, add negative keywords
YouTube cost per registration | Below ₹500 | Above ₹900 after ₹3,000 spent | Change the first 5 seconds of the video
Landing page conversion | Above 12% | Below 8% | Change headline or shorten the form
Right audience (manager+ title and bill filled) | Above 50% | Below 35% | Tighten Meta interests, shift money to LinkedIn
Winning ad | Cost 30% below target |  | Raise budget 20% every 3 days
Ad fatigue (CTR drops 30% from its best) |  | CTR falls 30% | Swap in a new ad version
Show-up rate on the day | Above 25% |  | Learning for the next webinar

## What-If
What-if: what happens if things go better or worse
Total all-in budget for 200 live attendees, depending on show-up rate and ad costs. Edit the blue headers to test other values.
Total budget (₹, all-in) for 200 live attendees
Show-up rate ↓ / Ad cost change → | -20% | 0% | 20% | 40%
20% | 594120 | 731400 | 868680 | 1005960
25% | 484296 | 594120 | 703944 | 813768
30% | 411263.04 | 502828.8 | 594394.56 | 685960.32
35% | 359096.64 | 437620.8 | 516144.96 | 594669.12
Expected case = 25% show-up and +0% ad cost change (this matches the Channel Plan total, up to rounding).
Registrations needed at each show-up rate
Show-up rate | Registrations needed | Ad spend at expected cost (₹)
20% | 1000 | 536250
25% | 800 | 429000
30% | 667 | 357678.75
35% | 572 | 306735
Takeaway: show-up rate matters as much as ad cost. Every 5 points of show-up we gain saves lakhs, which is why the reminder plan is not optional.

## Glossary
Glossary: plain-English meaning of every term
Term | Meaning
Impression | One time an ad is shown on someone's screen.
CTR (click-through rate) | Out of 100 people who see the ad, how many click. 1% = 1 in 100.
Conversion rate | Out of 100 people who click, how many fill the registration form.
Registration | Someone who filled the form. Not yet an attendee.
Cost per registration (CPR) | Ad money spent ÷ number of registrations.
Show-up rate | Out of 100 registrations, how many actually join live.
Cost per live attendee | Total budget ÷ number of people who attend live. The number that matters.
Retargeting | Showing ads again to people who already visited our page or watched our video.
Lead Gen Form / Lead form | A form inside LinkedIn or Meta that is pre-filled with the person's details. Higher sign-ups than a website form.
Thought Leader Ad (LinkedIn) | The company pays to promote a post from the CEO's or CTO's personal profile. Usually cheaper and more trusted than company-page ads.
Pixel / Insight Tag / Google tag | Small tracking codes on the landing page that tell each ad platform who registered, so it can find more people like them.
UTM | A tag at the end of a link that shows which ad a registration came from.
Test buffer | Money we expect to lose on ads that don't work in week 1. The price of finding the winners.
Ad fatigue | When the same people see an ad too often and stop clicking. Fix: new ad version.